Minutes for:   Blue Group

Date :

11/15/2004

Time:

7:00 – 9:05

Attending:

Brian, Ryan, John, David, Valentina, Jeff, Patrick

- Funding

  - NSF

    - Technology in Education

- WBS

  - Split Up between people

  - Patrick needs Budget Stuff

  - Plans

    - Management Plan

      - Ryan

      - Us and 2 consultants

    - Market Plans

      - Valentina

    - Evaluation Plan

      - Jeff

- Built-in Distribution

  - FTP, Filesend and other simple ways

  - No 3rd Party “integration”

    - Maybe later on

      - Blackboard and lotus Plugin

- Feasibility Section

  - Valentina – send to Patrick the updated feas. Presentation

- NSF

  - What Topic under NSF?

    - Education Directorate

- Competition

  - Teletechnet – Camera section

- Jeff leaves to print WBS’s

- Convert plans to Gantt Charts

  - David

- Tasks

  - Manhours  and people

- Look over WBS (long time)

  - # of men x Hours

  - Make  Choices a Milestone

  - 20 hr/ week (we’re parttimers)

  - Should we include Purchasing?

  - Talk about selling of boards

    - How much?

Minutes Type: 11/15/2004

WBS Work

Some Numbers

Phase 1

359 Man Hours

23   Consulting Hours

Prototyping

359 Man Hours

0 Consulting Hours

Development  Phase II

278 Man Hours

84 Consulting

Student Audio/Visual E-tool

Work Breakdown Structure

1000 Project Management

1100 Quality Assurance

1200 Risk Management

1300 Personnel Management

1310 Consultation

1311 Education Consultant

1312 Technical Planning Consultant

2000 Planning – Phase I

2100 Component Technology Choices

2110 Hardware Choices

2111 Whiteboard Choice   3 x 9 hrs

2112 Microphone Choice  2 x 4 hrs

2113 Integration Choices  2 x 9 hrs

2114 Technical Consultation   6 hrs

2120 Software Choices

2121 Audio Compression Choice  2 x 2 hrs

2122 Graphic Algorithm Choice  2 x 4 hrs

2123 Synchronization Choice  2 x 3 hrs

2124 Distribution Choices  2 x 6 hrs

2125 Playback Platform Choice  2 x 2 hrs

2126 Technical Consultation  5 hrs

2200 Identify Requirements

2210 Identify Recording Requirements

2211 Identify Hardware Requirements for Recording

2211.1 Identify Pen Requirements  1 x 1 hrs

2211.2 Identify Eraser Requirements  1 x 1 hrs

2211.3 Identify Board Requirements  2 x 2 hrs

2211.4 Identify Computer Requirements  1 x 1 hrs

2211.5 Identify Microphone Requirements  1 x1 hrs

2211.6 Identify Connection Requirements  1 x 1 hrs

2212 Identify Software Requirements for Recording

2212.1 Identify User Interface Requirements  3 x 16 hrs

2212.2 Identify Audio Recording Requirements  2 x 4 hrs

2212.3 Identify Graphic Recording Requirements  3 x 6 hrs

2212.4 Identify Synchronization Requirements  2 x 3 hrs

2212.5 Identify Storage Requirements  1 x 2 hrs

2212.6 Identify Software Installation Requirements  2 x 2 hrs

2212.7 Identify Software Upgrade Requirements  2 x 2 hrs

2212.8 Identify Software Removal Requirements 2 x 2 hrs

2212.9 Identify Distribution Requirements

2212.9.1 Analyze Distribution Interfaces  3 x 3 hrs

2212.9.2 Identify Distribution Software Requirements  3 x 3 hrs

2230 Identify Playback Requirements

2231 Identify User Interface Requirements  3 x 8 hrs

2232 Identify File Access Requirements  2 x 3 hrs

2233 Identify Audio Decoding Requirements  2 x 4 hrs

2234 Identify Graphic Decoding Requirements  2 x 4 hrs

2235 Identify Graphic Display Requirements  3 x 6 hrs

2236 Identify Audio Replay Requirements  2 x 3 hrs

2300 Identify Potential Technology Risks

2310 Hardware Failures

2311 Potential Whiteboard Failures  3 x 2 hrs

2312 Potential Microphone Failures  3 x 1 hrs

2313 Potential Computer Failures  3 x 2 hrs

2314 Potential Connection Failures  3 x 1 hrs

2320 Software Failures

2321 Potential Recording Failures

2321.1 Potential Encoding Failures  3 x 5 hrs

2322 Potential Distribution Failures  3 x 2 hrs

2323 Potential Playback Failures

2323.1 Potential Decoding Failures  3 x 4 hrs

2330 Technical Consultation  12 hrs

2400 Identify Concept Test Requirements

2410 Identify Key Hardware Demonstrations Necessary

2411 Design Whiteboard Concept Demonstrations  2 x 2 hrs

2412 Design Connection Concept Demonstrations  2 x 1 hrs

2413 Design Microphone Concept Demonstrations  2 x 1 hrs

2420 Identify Key Software Demonstrations Necessary

2421 Design Recording Concept Demonstration  3 x 3 hrs

2422 Design Distribution Concept Demonstration  3 x 2 hrs

2423 Design Playback Concept Demonstration  2 x 2 hrs

2430 Create Real World Test Scenario  {40 hours (Moved to Phase 2) }

2431 Educational Consultant

3000 Prototyping – Phase I

3100 Develop Prototype Software

3110 Develop Recording Software

3111 User Interface

3111.1 Recording Interface  10 hrs

3111.2 Distribution Interface  10 hrs

3112 Whiteboard Interface  60 hrs

3113 Microphone Interface  20 hrs

3114 Graphics Encoding  60 hrs

3114 Audio Encoding  20 hrs

3115 Audio/Video Synchronization  20 hrs

3116 File Storage

3116.1 Create File Storage Protocol  30 hrs

3120 Develop Playback Software

3121 User Interface  20 hrs

3122 File Reading 10 hrs

3123 Audio Playback 20 hrs

3124 Graphics Playback  30 hrs

3200 Develop Prototype Hardware

3210 Integrate Wireless Microphone to Computer  5 hrs

3220 Integrate Whiteboard to Computer 5 hrs

3400 Concept Testing

3410 Hardware Concept Testing

3411 Execute Whiteboard Test  3 x 2 hrs

3412 Execute Microphone Test  3 x 1 hrs

3413 Execute Connection Test  3 x 1 hrs

3420 Software Concept Testing

3421 Execute Recording Concept Test   3 x 4 hrs

3422 Execute Distribution Concept Test  3 x 2 hrs

3423 Execute Playback Concept Test  3 x 3 hrs

3430 Real World Scenario Testing   {Removed}

3431 Educational Consultant

4000 Development – Phase II

4100 Design Final Product Evaluation Criteria   {All of 4100 Section  40 Hours of  Educational Consultant}

4110 Design Real World Field Test

4120 Create Field Test Student Survey

4121 Evaluate Playback Usability

4122 Evaluate Playback Helpfulness

4123 Identify Playback Problems

4124 Evaluate Additional Playback Qualities

4130 Create Field Test Teacher Survey

4131 Evaluate Hardware Usability

4132 Evaluate Hardware Durability

4133 Evaluate Recording Usability

4134 Evaluate Distribution Usability

4135 Evaluate Classroom Role

4136 Identify Problems

4137 Evaluate Additional Qualities

4200 Develop Prototype Software

4210 Develop Recording Software

4211 User Interface

4211.1 Recording Interface  10 hrs

4211.2 Distribution Interface  10 hrs

4212 Whiteboard Interface  60 hrs

4213 Microphone Interface  20 hrs

4214 Graphics Encoding   60 hrs

4214 Audio Encoding  20 hrs

4215 Audio/Video Synchronization 20 hrs

4216 File Storage

4216.1 Create File Storage Protocol  30 hrs

4220 Develop Playback Software

4221 User Interface  20 hrs

4222 File Reading  10 hrs

4223 Audio Playback  20 hrs

4224 Graphics Playback  30 hrs

4300 Develop Prototype Hardware

4310 Integrate Wireless Microphone to Computer  5 hrs

4320 Integrate Whiteboard to Computer  5 hrs

4300 Testing and Evaluation

4310 Execute Field Tests             Consultant

4320 Execute Student Surveys     Same Consultant

4330 Execute Teacher Surveys    Same Consultant  = 40 hrs

4340 Evaluate Success    7 x 4 hrs  +  1 consultant x 4 hrs

5000 Production – Phase III

5100 Manufacturing

5200 Marketing

5300 Shipping

5400 Documentation

5410 Hardware

5411 Hardware Installation Documentation

5412 Hardware Operation Documentation

5420 Software

5421 Recording Software

5421.1 Installation Documentation

5421.2 Operation Documentation

5422 Playback Software

5422.1 Operation Documentation