- Specific Aims

According to a recent Price Waterhouse Coopers study conducted to uncover the reasons for increases in health care spending over the last decade from 1997 to 2001, spending on hospital care increased by $83.6 Billion and hospital gross margins have declined annually every year since 1997.  The study leads one to the conclusion that Hospitals are being asked to do more with less. 3

Of the total of all health care costs in American hospitals wages and benefits for nurses account for 36%, or $166.4 Billion annually. 3  That figure is derived by taking the total cost of all health care wages and benefits ($462 Billion), of which 36% is nurses' wages and benefits.

Additionally there are currently 5,794 hospitals registered with the American Hospital Association with a total of 975,962 registered beds. 2  Our estimate based on these statistics is that there is approximately 10 pieces of mobile medical equipment in a hospital per registered bed.  These items would include EKGs, portable X-Ray machines, crash carts, IV poles, wheelchairs, mobile beds, glucometers, ultrasound machines, transfusers, drug carts, and many other pieces of equipment.  Additionally, almost every piece of hospital equipment that is not physically installed in a room is mobile.  All hospital equipment is very costly.

According to another recent study performed by Mark Murphy showed that finding needed equipment is one of the top ten most wasteful activities at hospitals. 1  Therefore, up to the minute inventory tracking is a real problem in hospitals all across America today.

The goal of the STATag project is to enable hospitals to eliminate waste, reduce operating costs, and stay in the business of providing health care to the community.

Digital inventory system’s solution for reducing cost in hospitals is the STATag.  It is a Real Time Inventory Tracking system that will reduce the man hours needed to search for equipment, lower operating costs and increase staff efficiency in maintaining medical devices.  All this is accomplished using the five modules contained inside STATag, the user interface and a database server.

STATags will reduce the effort needed to locate a device by displaying its location on an easy  to use interface.  No longer will hospital staff have to go room to room to locate medical devices. All the staff will have to do is query the database for the item they desire and a picture diagram will appear on the screen, showing the locations of the device they queried. The viewer of the diagram will be able to tell which device is not in use because it will show up active on the screen.  From there all the staff member will have to do is go and get the item because the floor and room location of the device will be specified in the diagram.

In addition to reducing searching efforts, operation cost and staff efficiency in maintaining the equipment will be affected.  The type of reports this system will generate will give insight to the duration of time they had a particular item, price by usage, inventory, equipment utilization, and missing equipment report

The STATag is capable of impacting the hospital community in this fashion because of the hardware components.  IEEE 802.15.4 is a self configuring system capable of communicating in noisy environment using a minute amount of power.  We use flash ram memory to back up the information gained in the environments where the communication signal may not be to strong.  In addition to this, we have a movement module that tracks the location of the device as it moves around the hospital.  All these components together provide the environment the type of communication that will be productive in a hospital environment.

The Phase I goals are:

- Construction and operation of a lab prototype of the STATag.  The prototype will demonstrate network detection, network auto-configuration, and communication between other lab prototypes.  Further, the lab prototype will be able to determine its current position using on-board sensors.

- Completion of the detailed specification for the production of the STATag.

- Background and Significance

From 1997 to 2001, spending on hospital care increased by $83.6 Billion. 3  Hospital gross margins have also declined annually every year since 1997. 3  This is due in large part to higher wages due to nurse shortages and a higher volume of patients.  By 2003, 57% of total hospital expenses were due to wages and benefits. For nurses alone, wages and benefits account for 36% of all hospital costs. 3   With this in mind, a real problem is at hand.  Hospitals have a history of losing and spending unnecessary money.

This money is wasted consequently on inefficiency of nurses and hospital staff.  From our studies, 35-60% of a nurse’s time is wasted on searching for equipment, clarifying orders, and entering redundant information.  All together this cost of inefficiency rounds in at about $58 - $99 billion annually.  At this point, hospitals need to reduce total costs in order to increase profitability.

In the near future, profitability of hospitals will become increasingly difficult as the Baby Boomer generation moves to retirement.  This shift of the largest population segment will cause:

- A more severe shortage of nurses.  The number of nurses approaching retirement age is much greater than the number of nurses currently in training.  This will result in greater upward pressure on nurse’s wages.

- Increased patients.  As the Baby Boomers continue to age, they will account for growing percentage of patients requiring health care.

- Decreased reimbursements.  The shift of the Baby Boomers from private health insurance to Medicare and Medicaid will drastically reduce the amount of money that hospitals receive in exchange for their services.  This is the effect of private health insurance paying approximately 90% of costs vs. Medicare and Medicaid paying only 45%.

- Preliminary Studies

Mark Murphy of the Murphy Leadership Institute found that reducing wasteful work results in an increase in the operating margin.1  It is this fact that the STATag will leverage to accomplish its goals of enabling hospitals to eliminate waste, reduce operating costs, and stay in the business of providing health care to the community.

Discussions with Cindy Jimmerson, a national lecturer on hospital efficiency, revealed that up to 65% of nurses’ time is wasted searching for equipment, entering redundant information, and clarifying orders.  In one example, eliminating the need to search for equipment (a glucometer) was found to save the nurse involved 13 minutes, for each patient.4

The principle of “Dead Reckoning” has been proved in such areas as NASA’s space shuttle program.  However, until recently, the technology has been too expensive to practical for large scale adoption, but advances in Micro-Electro-Mechanical Systems (MEMS) have changed that.

The technology to needed to build the STATag is already commercially available.  The basic building blocks that make the STATag function are the MEMS accelerometers, MEMS gyroscopes, 802.15.4 radios, and the ZigBee protocol standard.

- Research Designs and Methods

The STATag project will be broken down into four phases.  The overall objective of our multiple phase work breakdown structure is to design, develop, test, evaluate, benchmark and (deploy) bring to production release an equipment tagging system that will affectively monitor hospital devices. This project will be broken into the following four phases:

Phase 0 - Establish the feasibility and technical ability to produce STATag.  Phase 0 will consist of seven major tasks.  Following is a list of specific tasks that will address the key objectives of phase 0 research.

- Develop an initial concept and a starting point.

- Select a project topic to develop further.

- Research the topic to gain background knowledge of the ideal.

- Research the feasibility of our topic.

- Research the milestones that will define our coarse schedule.

- Research all the components of an SBIR grant proposal write-up.

- Develop STATag’s webpage.

Phase 1 - Develop a lab prototype and all its specifications.  Phase 1 will consist of five major tasks.  Following is a list of specific tasks that will address the key objectives of phase 1 research.

- Hire personal such as a technical writer and a software engineer to maintain integrity in all aspects of STATag’s production.

- Specify, implement, test, and design our lab prototype. In addition to this we will develop, execute, and evaluate test problems to demonstrate the feasibility (compatibility) of the software and hardware components.

- Update the webpage information.

- Prepare phase two grant proposal.

- Submit phase two grant proposal.

Phase 2 - Establish, in a hospital, a real world functioning model.  Phase 2 will consist of nine major.   Following is a list of specific tasks that will address the key objectives of phase two research.

- Hire additional staff.

- Develop a software design and a plan for integration.

- Design a software web interface.

- Specify, implement, test, and design for real world integration. In addition to this we will develop, execute, and evaluate test problems to demonstrate interface compatibility of the software and hardware components.

- Develop user and testing documentation.

- Produce finalized result of the extensive software testing.

- Contract a legal representative.

- Begin the three phase real world installment of STATag.

- Develop a market plan for the continuation of DIS without grant assistance.

Phase 3 – Achieve self-sustaining.  Phase 3 will consist of nine major tasks. Following is a list of specific tasks that will address the key objectives of phase 3 research.

- We will hire additional staff.

- Produce Ramp up.

- Establish full production of STATag.

- Develop a support Department.

- Establish a support Department.

- Train installation engineers.

- Enhance our marketing and sales techniques.

- Establish ourselves in tradeshows.

- Develop an in-depth support team which will consist of updates, warranty and telephone support.

Work Breakdown Structure

| 1 | Phase 0 - Concept | 1/12/2004 8:00 | 5/3/2004 17:00 | 81 days |  |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Project Start | 1/12/2004 17:00 | 1/12/2004 17:00 | 0 days | Daniel Tubbs,Latricia Simon,Jason Sadler,Brian Easton,Francis Deligosa,Joseph Williams |
| 1.2 | Project Selection | 1/12/2004 8:00 | 2/11/2004 17:00 | 23 days |  |
| 1.2.1 | Project Topic Ideas | 1/12/2004 8:00 | 1/12/2004 17:00 | 1 day | Daniel Tubbs,Latricia Simon,Jason Sadler,Brian Easton,Francis Deligosa,Joseph Williams |
| 1.2.2 | Team Members Selected | 1/13/2004 8:00 | 1/15/2004 17:00 | 3 days | Daniel Tubbs[50%],Latricia Simon[50%],Jason Sadler[50%],Brian Easton[50%],Francis Deligosa[50%],Joseph Williams[50%] |
| 1.2.3 | Team Organization | 1/16/2004 8:00 | 1/22/2004 17:00 | 5 days | Daniel Tubbs[50%],Latricia Simon[50%],Jason Sadler[50%],Brian Easton[50%],Francis Deligosa[50%],Joseph Williams[50%] |
| 1.2.4 | Define Team Responsibilities | 1/23/2004 8:00 | 1/29/2004 17:00 | 5 days | Daniel Tubbs[50%],Latricia Simon[50%],Jason Sadler[50%],Brian Easton[50%],Francis Deligosa[50%],Joseph Williams[50%] |
| 1.2.5 | Individual Project Research | 1/13/2004 8:00 | 2/11/2004 17:00 | 22 days | Daniel Tubbs[50%],Latricia Simon[50%],Jason Sadler[50%],Brian Easton[50%],Francis Deligosa[50%],Joseph Williams[50%] |
| 1.2.6 | Individual Project Presentation | 2/11/2004 17:00 | 2/11/2004 17:00 | 0 days | Daniel Tubbs,Latricia Simon,Jason Sadler,Brian Easton,Francis Deligosa,Joseph Williams |
| 1.3 | Projects Research | 2/12/2004 8:00 | 2/17/2004 17:00 | 4 days |  |
| 1.3.1 | Projects Research | 2/12/2004 8:00 | 2/16/2004 17:00 | 3 days | Daniel Tubbs,Latricia Simon,Jason Sadler,Brian Easton,Francis Deligosa,Joseph Williams |
| 1.3.2 | Team Project Selection | 2/17/2004 8:00 | 2/17/2004 17:00 | 1 day | Daniel Tubbs,Latricia Simon,Jason Sadler,Brian Easton,Francis Deligosa,Joseph Williams |
| 1.4 | Feasibility Research | 2/18/2004 8:00 | 3/17/2004 17:00 | 21 days |  |
| 1.4.1 | Market Research | 2/18/2004 8:00 | 3/17/2004 17:00 | 21 days | Daniel Tubbs[25%],Latricia Simon[25%],Jason Sadler[20%],Brian Easton[25%],Francis Deligosa[25%],Joseph Williams[25%] |
| 1.4.2 | Risk Analysis | 2/18/2004 8:00 | 3/17/2004 17:00 | 21 days | Daniel Tubbs[25%],Latricia Simon[25%],Jason Sadler[20%],Brian Easton[25%],Francis Deligosa[25%],Joseph Williams[25%] |
| 1.4.3 | Research Competitors | 2/18/2004 8:00 | 3/17/2004 17:00 | 21 days | Daniel Tubbs[25%],Latricia Simon[25%],Jason Sadler[20%],Brian Easton[25%],Francis Deligosa[25%],Joseph Williams[25%] |
| 1.4.4 | Feasibility Presentation | 3/17/2004 17:00 | 3/17/2004 17:00 | 0 days | Daniel Tubbs,Latricia Simon,Jason Sadler,Brian Easton,Francis Deligosa,Joseph Williams |
| 1.5 | Milestone Research | 3/18/2004 8:00 | 4/14/2004 17:00 | 20 days |  |
| 1.5.1 | Work break Down Structure | 3/18/2004 8:00 | 4/6/2004 17:00 | 14 days | Daniel Tubbs[75%],Latricia Simon[75%],Jason Sadler[60%],Brian Easton[75%],Francis Deligosa[75%],Joseph Williams[75%] |
| 1.5.2 | Budget | 4/7/2004 8:00 | 4/9/2004 17:00 | 3 days | Brian Easton[37%],Joseph Williams[75%] |
| 1.5.3 | ROI Analysis | 4/12/2004 8:00 | 4/14/2004 17:00 | 3 days | Brian Easton[75%] |
| 1.5.4 | Marketing Plan | 4/7/2004 8:00 | 4/9/2004 17:00 | 3 days | Jason Sadler[60%] |
| 1.5.5 | Finance Plan | 4/7/2004 8:00 | 4/9/2004 17:00 | 3 days | Brian Easton[37%] |
| 1.5.6 | Management Plan | 4/7/2004 8:00 | 4/13/2004 17:00 | 5 days | Francis Deligosa[75%] |
| 1.5.7 | Evaluation Plan | 4/7/2004 8:00 | 4/9/2004 17:00 | 3 days | Latricia Simon[75%] |
| 1.5.8 | Milestone Presentation | 4/14/2004 17:00 | 4/14/2004 17:00 | 0 days | Daniel Tubbs,Latricia Simon,Jason Sadler,Brian Easton,Francis Deligosa,Joseph Williams |
| 1.6 | SBIR Research | 2/18/2004 8:00 | 5/3/2004 17:00 | 54 days |  |
| 1.6.1 | SBIR Grant Proposal | 2/18/2004 8:00 | 5/3/2004 17:00 | 54 days | Daniel Tubbs[25%],Latricia Simon[25%],Jason Sadler[20%],Brian Easton[25%],Francis Deligosa[25%],Joseph Williams[25%] |
| 1.6.2 | SBIR Grant Application & Presentation | 5/3/2004 17:00 | 5/3/2004 17:00 | 0 days | Daniel Tubbs,Latricia Simon,Jason Sadler,Brian Easton,Francis Deligosa,Joseph Williams |
| 1.7 | Website | 2/18/2004 8:00 | 5/3/2004 17:00 | 54 days |  |
| 1.7.1 | Website Draft | 2/18/2004 8:00 | 3/2/2004 17:00 | 10 days | Jason Sadler[20%] |
| 1.7.2 | Website Update 1 | 3/18/2004 8:00 | 4/6/2004 17:00 | 14 days | Jason Sadler[20%] |
| 1.7.3 | Website Update 2 | 4/15/2004 8:00 | 5/3/2004 17:00 | 13 days | Jason Sadler[20%] |
| 1.7.4 | Website Complete | 5/3/2004 17:00 | 5/3/2004 17:00 | 0 days | Jason Sadler |
| 2 | Phase 1 - Proof of Concept | 8/23/2004 8:00 | 12/10/2004 17:00 | 80 days |  |
| 2.1 | Hire Personnel | 8/23/2004 8:00 | 9/17/2004 17:00 | 20 days | Joseph Williams[10%] |
| 2.2 | Build Lab Prototype | 8/23/2004 8:00 | 12/3/2004 13:39 | 74.58 days |  |
| 2.2.1 | Prototype Documentation | 8/23/2004 8:00 | 9/10/2004 17:00 | 15 days |  |
| 2.2.1.1 | Prototype Specification | 8/23/2004 8:00 | 9/7/2004 17:00 | 12 days | Daniel Tubbs,Latricia Simon[25%],Francis Deligosa[25%],Drafter[21%] |
| 2.2.1.2 | QA | 9/8/2004 8:00 | 9/8/2004 17:00 | 1 day | Latricia Simon |
| 2.2.1.3 | Rework | 9/9/2004 8:00 | 9/10/2004 17:00 | 2 days | Daniel Tubbs,Latricia Simon[25%],Francis Deligosa[25%] |
| 2.2.1.4 | Prototype Specifications (Draft) Complete | 9/10/2004 17:00 | 9/10/2004 17:00 | 0 days | Daniel Tubbs,Latricia Simon[25%],Francis Deligosa[25%] |
| 2.2.1.5 | Prototype Specification Complete | 9/10/2004 17:00 | 9/10/2004 17:00 | 0 days |  |
| 2.2.2 | High Level Design | 9/13/2004 8:00 | 10/8/2004 17:00 | 20 days |  |
| 2.2.2.1 | Vendor Selection | 9/13/2004 8:00 | 9/17/2004 17:00 | 5 days | Daniel Tubbs[25%],Francis Deligosa[90%] |
| 2.2.2.2 | Parts Selection | 9/20/2004 8:00 | 9/24/2004 17:00 | 5 days | Daniel Tubbs[25%],Francis Deligosa[90%] |
| 2.2.2.3 | Acquire Parts | 9/27/2004 8:00 | 10/8/2004 17:00 | 10 days | Francis Deligosa[10%],Parts Vendor |
| 2.2.2.4 | Parts Acquired | 10/8/2004 17:00 | 10/8/2004 17:00 | 0 days |  |
| 2.2.3 | Develop Prototype | 9/20/2004 8:00 | 11/19/2004 13:39 | 44.58 days |  |
| 2.2.3.1 | Computer Interface Module | 9/20/2004 8:00 | 10/29/2004 13:39 | 29.58 days |  |
| 2.2.3.1.1 | Design Circuits | 9/20/2004 8:00 | 10/1/2004 17:00 | 10 days | Daniel Tubbs[90%],Computer Engineer[39%] |
| 2.2.3.1.2 | Build Circuit | 10/13/2004 13:39 | 10/15/2004 13:39 | 2 days | Daniel Tubbs[90%] |
| 2.2.3.1.3 | Test Circuit | 10/19/2004 13:39 | 10/21/2004 13:39 | 2 days | Daniel Tubbs[90%] |
| 2.2.3.1.4 | QA | 10/21/2004 13:39 | 10/22/2004 13:39 | 1 day | Latricia Simon |
| 2.2.3.1.5 | Rework | 10/28/2004 13:39 | 10/29/2004 13:39 | 1 day | Daniel Tubbs[90%] |
| 2.2.3.1.6 | Computer Interface Complete | 10/29/2004 13:39 | 10/29/2004 13:39 | 0 days |  |
| 2.2.3.2 | Dead Reckoning Module | 9/23/2004 8:00 | 11/1/2004 13:39 | 27.58 days |  |
| 2.2.3.2.1 | Design Circuits | 9/23/2004 8:00 | 10/11/2004 13:39 | 10 days | Daniel Tubbs[90%],Computer Engineer[39%] |
| 2.2.3.2.2 | Build Circuit | 10/15/2004 13:39 | 10/19/2004 13:39 | 2 days | Daniel Tubbs[90%] |
| 2.2.3.2.3 | Test Circuit | 10/25/2004 13:39 | 10/27/2004 13:39 | 2 days | Daniel Tubbs[90%] |
| 2.2.3.2.4 | QA | 10/27/2004 13:39 | 10/28/2004 13:39 | 1 day | Latricia Simon |
| 2.2.3.2.5 | Rework | 10/29/2004 13:39 | 11/1/2004 13:39 | 1 day | Daniel Tubbs[90%] |
| 2.2.3.2.6 | Dead Reckoning Module Complete | 11/1/2004 13:39 | 11/1/2004 13:39 | 0 days |  |
| 2.2.3.3 | 802.15.4 Module | 9/20/2004 8:00 | 10/28/2004 13:39 | 28.58 days |  |
| 2.2.3.3.1 | Design Circuits | 9/20/2004 8:00 | 9/29/2004 17:00 | 6 days | Daniel Tubbs[90%],Computer Engineer[39%] |
| 2.2.3.3.2 | Build Circuit | 10/11/2004 13:39 | 10/13/2004 13:39 | 2 days | Daniel Tubbs[90%] |
| 2.2.3.3.3 | Test Circuit | 10/21/2004 13:39 | 10/25/2004 13:39 | 2 days | Daniel Tubbs[90%] |
| 2.2.3.3.4 | QA | 10/25/2004 13:39 | 10/26/2004 13:39 | 1 day | Latricia Simon |
| 2.2.3.3.5 | Rework | 10/27/2004 13:39 | 10/28/2004 13:39 | 1 day | Daniel Tubbs[90%] |
| 2.2.3.3.6 | 802.15.4 Module Complete | 10/28/2004 13:39 | 10/28/2004 13:39 | 0 days |  |
| 2.2.3.4 | Software Interface | 10/29/2004 13:39 | 11/18/2004 13:39 | 14 days |  |
| 2.2.3.4.1 | Design Software Interface | 10/29/2004 13:39 | 11/10/2004 13:39 | 8 days | Brian Easton[90%],Daniel Tubbs[10%] |
| 2.2.3.4.2 | Build Software Interface | 11/10/2004 13:39 | 11/12/2004 13:39 | 2 days | Brian Easton[90%],Daniel Tubbs[10%] |
| 2.2.3.4.3 | Test Software Interface | 11/12/2004 13:39 | 11/16/2004 13:39 | 2 days | Brian Easton[90%],Daniel Tubbs[10%] |
| 2.2.3.4.4 | QA | 11/16/2004 13:39 | 11/17/2004 13:39 | 1 day | Latricia Simon |
| 2.2.3.4.5 | Rework | 11/17/2004 13:39 | 11/18/2004 13:39 | 1 day | Brian Easton[90%],Daniel Tubbs[10%] |
| 2.2.3.4.6 | Software Interface Complete | 11/18/2004 13:39 | 11/18/2004 13:39 | 0 days |  |
| 2.2.3.5 | Integrate Components | 11/1/2004 13:39 | 11/19/2004 13:39 | 14 days |  |
| 2.2.3.5.1 | Design Circuits | 11/1/2004 13:39 | 11/11/2004 13:39 | 8 days | Daniel Tubbs[90%],Computer Engineer[39%] |
| 2.2.3.5.2 | Build Circuit | 11/11/2004 13:39 | 11/15/2004 13:39 | 2 days | Daniel Tubbs[90%] |
| 2.2.3.5.3 | Test Circuit | 11/15/2004 13:39 | 11/17/2004 13:39 | 2 days | Daniel Tubbs[90%] |
| 2.2.3.5.4 | QA | 11/17/2004 13:39 | 11/18/2004 13:39 | 1 day | Latricia Simon |
| 2.2.3.5.5 | Rework | 11/18/2004 13:39 | 11/19/2004 13:39 | 1 day | Daniel Tubbs[90%] |
| 2.2.3.5.6 | Lab Prototype Built | 11/19/2004 13:39 | 11/19/2004 13:39 | 0 days | Daniel Tubbs[90%] |
| 2.2.4 | Prototype Testing | 11/19/2004 13:39 | 11/25/2004 13:39 | 4 days |  |
| 2.2.4.1 | Test Prototype | 11/19/2004 13:39 | 11/23/2004 13:39 | 2 days | Daniel Tubbs[90%],Brian Easton[90%] |
| 2.2.4.2 | QA | 11/23/2004 13:39 | 11/24/2004 13:39 | 1 day | Latricia Simon |
| 2.2.4.3 | Rework | 11/24/2004 13:39 | 11/25/2004 13:39 | 1 day | Daniel Tubbs[90%],Brian Easton[90%] |
| 2.2.4.4 | Lab Prototype Testing Complete | 11/25/2004 13:39 | 11/25/2004 13:39 | 0 days |  |
| 2.2.5 | Update Design Specifications | 11/25/2004 13:39 | 12/2/2004 13:39 | 5 days | Daniel Tubbs[90%] |
| 2.2.6 | Product Specification (final) Complete | 12/2/2004 13:39 | 12/2/2004 13:39 | 0 days | Daniel Tubbs[90%] |
| 2.2.7 | Prototype Demonstration | 12/2/2004 13:39 | 12/3/2004 13:39 | 1 day | Daniel Tubbs,Latricia Simon,Jason Sadler,Brian Easton,Francis Deligosa,Joseph Williams |
| 2.3 | Webpage | 11/18/2004 13:39 | 12/2/2004 13:39 | 10 days | Jason Sadler[50%] |
| 2.4 | SBIR Phase 2 Application | 8/23/2004 8:00 | 12/10/2004 17:00 | 80 days | Daniel Tubbs[10%],Latricia Simon[10%],Jason Sadler[10%],Brian Easton[10%],Francis Deligosa[10%],Joseph Williams[10%] |
| 2.5 | SBIR Phase 2 Application Submitted | 12/10/2004 17:00 | 12/10/2004 17:00 | 0 days | Daniel Tubbs,Latricia Simon,Jason Sadler,Brian Easton,Francis Deligosa,Joseph Williams |
| 3 | Phase 2 - Product Development | 1/3/2005 8:00 | 5/2/2006 17:00 | 347 days |  |
| 3.1 | Obtain SBA Loan | 1/3/2005 8:00 | 2/25/2005 17:00 | 40 days | Brian Easton[10%] |
| 3.2 | SBA Loan Obtained | 2/25/2005 17:00 | 2/25/2005 17:00 | 0 days |  |
| 3.3 | Hire Staff - Phase 2 | 4/5/2005 8:00 | 5/4/2005 17:00 | 20 days | Joseph Williams[10%] |
| 3.4 | Software Development | 1/3/2005 8:00 | 9/28/2005 13:02 | 192.5 days |  |
| 3.4.1 | Software Design | 1/3/2005 8:00 | 2/11/2005 17:00 | 30 days | Francis Deligosa[50%],Joseph Williams |
| 3.4.2 | Develop Integration Plan | 1/3/2005 8:00 | 2/1/2005 17:00 | 20 days | Latricia Simon[90%],Daniel Tubbs |
| 3.4.3 | Database Development | 2/14/2005 8:00 | 5/9/2005 17:00 | 61 days |  |
| 3.4.3.1 | Database Selection | 2/14/2005 8:00 | 2/25/2005 17:00 | 10 days | Joseph Williams,Jason Sadler |
| 3.4.3.2 | Finalize Database Design | 3/1/2005 8:00 | 3/7/2005 17:00 | 5 days | Joseph Williams |
| 3.4.3.3 | Develop Assets Table | 4/4/2005 8:00 | 4/8/2005 17:00 | 5 days | Jason Sadler |
| 3.4.3.4 | Develop History Table | 3/29/2005 8:00 | 4/4/2005 17:00 | 5 days | Joseph Williams |
| 3.4.3.5 | QA | 4/11/2005 8:00 | 4/11/2005 17:00 | 1 day | Latricia Simon[90%] |
| 3.4.3.6 | Rework | 4/12/2005 8:00 | 4/13/2005 17:00 | 2 days | Joseph Williams |
| 3.4.3.7 | Reports | 2/22/2005 8:00 | 5/9/2005 17:00 | 55 days |  |
| 3.4.3.7.1 | Finalize Report Design | 2/22/2005 8:00 | 3/4/2005 17:00 | 9 days | Joseph Williams,Jason Sadler |
| 3.4.3.7.2 | List Reports Here! | 3/7/2005 8:00 | 3/11/2005 17:00 | 5 days | Jason Sadler |
| 3.4.3.7.3 | List Reports Here! | 3/8/2005 8:00 | 3/14/2005 17:00 | 5 days | Joseph Williams |
| 3.4.3.7.4 | Cost Per Use Report | 3/14/2005 8:00 | 3/18/2005 17:00 | 5 days | Jason Sadler |
| 3.4.3.7.5 | Aging Report | 3/15/2005 8:00 | 3/21/2005 17:00 | 5 days | Joseph Williams |
| 3.4.3.7.6 | Inventory Report | 3/21/2005 8:00 | 3/25/2005 17:00 | 5 days | Jason Sadler |
| 3.4.3.7.7 | Missing Equipment Report | 3/22/2005 8:00 | 3/28/2005 17:00 | 5 days | Joseph Williams |
| 3.4.3.7.8 | Equipment Utilization Report | 3/28/2005 8:00 | 4/1/2005 17:00 | 5 days | Jason Sadler |
| 3.4.3.7.9 | QA | 4/4/2005 8:00 | 4/5/2005 17:00 | 2 days | Latricia Simon[90%] |
| 3.4.3.7.10 | Rework | 5/5/2005 8:00 | 5/9/2005 17:00 | 3 days | Joseph Williams |
| 3.4.3.8 | Database Development Complete | 5/9/2005 17:00 | 5/9/2005 17:00 | 0 days |  |
| 3.4.4 | Web Interface | 2/14/2005 8:00 | 8/11/2005 9:02 | 128.13 days |  |
| 3.4.4.1 | Web server Selection | 2/14/2005 8:00 | 3/7/2005 9:02 | 10 days | Francis Deligosa[90%],Software Engineer |
| 3.4.4.2 | Finalize Web Interface Design | 3/7/2005 9:02 | 3/21/2005 9:02 | 10 days | Francis Deligosa[90%],Software Engineer |
| 3.4.4.3 | Mapping Module | 3/21/2005 9:02 | 4/18/2005 9:02 | 20 days | Francis Deligosa |
| 3.4.4.4 | Setup Module | 3/21/2005 9:02 | 4/18/2005 9:02 | 20 days | Software Engineer |
| 3.4.4.5 | Inventory Entry Module | 4/18/2005 9:02 | 5/16/2005 9:02 | 20 days | Software Engineer |
| 3.4.4.6 | Alarm Module | 4/18/2005 9:02 | 8/4/2005 9:02 | 15 days | Francis Deligosa |
| 3.4.4.7 | Help Screens | 5/16/2005 9:02 | 5/30/2005 9:02 | 10 days | Software Engineer |
| 3.4.4.8 | QA | 8/4/2005 9:02 | 8/8/2005 9:02 | 2 days | Latricia Simon[90%] |
| 3.4.4.9 | Rework | 8/8/2005 9:02 | 8/11/2005 9:02 | 3 days | Francis Deligosa[90%],Software Engineer |
| 3.4.4.10 | Web Interface Development Complete | 8/11/2005 9:02 | 8/11/2005 9:02 | 0 days |  |
| 3.4.5 | Integration Testing | 8/11/2005 9:02 | 9/28/2005 13:02 | 34.38 days |  |
| 3.4.5.1 | Hardware Testing | 8/11/2005 9:02 | 9/1/2005 9:02 | 15 days | Daniel Tubbs |
| 3.4.5.2 | Database Testing | 8/11/2005 9:02 | 9/1/2005 9:02 | 15 days | Francis Deligosa[90%],Software Engineer |
| 3.4.5.3 | Reports Testing | 9/1/2005 9:02 | 9/22/2005 9:02 | 15 days | Francis Deligosa[90%],Software Engineer |
| 3.4.5.4 | Web Interface Testing | 8/11/2005 9:02 | 9/1/2005 9:02 | 15 days |  |
| 3.4.5.4.1 | Internet Explorer | 8/11/2005 9:02 | 8/18/2005 9:02 | 5 days | Joseph Williams,Jason Sadler |
| 3.4.5.4.2 | Netscape | 8/18/2005 9:02 | 8/25/2005 9:02 | 5 days | Joseph Williams,Jason Sadler |
| 3.4.5.4.3 | Pocket PC Testing | 8/25/2005 9:02 | 9/1/2005 9:02 | 5 days | Joseph Williams,Jason Sadler |
| 3.4.5.5 | QA | 9/1/2005 9:02 | 9/7/2005 9:02 | 4 days | Latricia Simon[90%] |
| 3.4.5.6 | Rework | 9/7/2005 9:02 | 9/28/2005 13:02 | 10 days | Francis Deligosa[90%],Jason Sadler,Joseph Williams,Daniel Tubbs |
| 3.4.5.7 | Integration Testing Complete | 9/28/2005 13:02 | 9/28/2005 13:02 | 0 days |  |
| 3.5 | Documentation | 1/3/2005 8:00 | 3/18/2005 15:59 | 54.87 days |  |
| 3.5.1 | User Manual | 1/3/2005 8:00 | 2/4/2005 15:59 | 24.87 days |  |
| 3.5.1.1 | Write User Manual | 1/3/2005 8:00 | 1/28/2005 15:59 | 10 days | Daniel Tubbs[75%],Brian Easton[10%],Francis Deligosa[10%],Technical Writer |
| 3.5.1.2 | QA | 1/28/2005 15:59 | 2/1/2005 15:59 | 2 days | Latricia Simon[90%] |
| 3.5.1.3 | Editing | 2/1/2005 15:59 | 2/4/2005 15:59 | 3 days | Daniel Tubbs[75%],Brian Easton[10%],Francis Deligosa[10%],Technical Writer |
| 3.5.2 | Training Manual | 2/4/2005 15:59 | 2/25/2005 15:59 | 15 days |  |
| 3.5.2.1 | Write Training Manual | 2/4/2005 15:59 | 2/18/2005 15:59 | 10 days | Daniel Tubbs[75%],Brian Easton[10%],Francis Deligosa[10%],Technical Writer |
| 3.5.2.2 | QA | 2/18/2005 15:59 | 2/22/2005 15:59 | 2 days | Latricia Simon[90%] |
| 3.5.2.3 | Editing | 2/22/2005 15:59 | 2/25/2005 15:59 | 3 days | Daniel Tubbs[75%],Brian Easton[10%],Francis Deligosa[10%],Technical Writer |
| 3.5.3 | Training CBT | 2/25/2005 15:59 | 3/18/2005 15:59 | 15 days |  |
| 3.5.3.1 | Create Training CBT | 2/25/2005 15:59 | 3/11/2005 15:59 | 10 days | Daniel Tubbs[75%],Brian Easton[10%],Francis Deligosa[10%],Technical Writer |
| 3.5.3.2 | QA | 3/11/2005 15:59 | 3/15/2005 15:59 | 2 days | Latricia Simon[90%] |
| 3.5.3.3 | Editing | 3/15/2005 15:59 | 3/18/2005 15:59 | 3 days | Daniel Tubbs[75%],Brian Easton[10%],Francis Deligosa[10%],Technical Writer |
| 3.5.3.4 | Documentation Complete | 2/25/2005 15:59 | 2/25/2005 15:59 | 0 days |  |
| 3.6 | Sample Production | 1/3/2005 8:00 | 4/26/2005 17:00 | 82 days |  |
| 3.6.1 | Contract Vendor Selection | 1/3/2005 8:00 | 1/21/2005 17:00 | 15 days | Francis Deligosa[50%],Daniel Tubbs[25%],Contract Manufacturer |
| 3.6.2 | Plastic Tooling | 1/21/2005 17:00 | 2/11/2005 17:00 | 15 days | Francis Deligosa[10%],Contract Manufacturer[33%] |
| 3.6.3 | Engineering | 1/21/2005 17:00 | 2/11/2005 17:00 | 15 days | Francis Deligosa[10%],Contract Manufacturer[33%] |
| 3.6.4 | Sample Run | 2/11/2005 17:00 | 3/25/2005 17:00 | 30 days | Francis Deligosa[10%],Contract Manufacturer[33%] |
| 3.6.5 | Hardware Testing | 3/28/2005 8:00 | 4/15/2005 17:00 | 15 days | Daniel Tubbs |
| 3.6.6 | QA | 4/18/2005 8:00 | 4/21/2005 17:00 | 4 days | Latricia Simon[90%] |
| 3.6.7 | Update Design Specification | 4/22/2005 8:00 | 4/26/2005 17:00 | 3 days | Daniel Tubbs[50%],Francis Deligosa[50%] |
| 3.6.8 | Design Finalized | 4/26/2005 17:00 | 4/26/2005 17:00 | 0 days |  |
| 3.7 | Finalize Production | 4/27/2005 8:00 | 1/10/2006 17:00 | 185 days |  |
| 3.7.1 | Plastic Tooling Update | 4/27/2005 8:00 | 6/7/2005 17:00 | 30 days | Francis Deligosa[10%],Contract Manufacturer[33%] |
| 3.7.2 | Engineering | 4/27/2005 8:00 | 5/17/2005 17:00 | 15 days | Francis Deligosa[10%],Contract Manufacturer[33%] |
| 3.7.3 | Sample Run 2 | 6/8/2005 8:00 | 7/19/2005 17:00 | 30 days | Francis Deligosa[10%],Contract Manufacturer[33%] |
| 3.7.4 | Retest Hardware | 7/20/2005 8:00 | 8/9/2005 17:00 | 15 days | Daniel Tubbs |
| 3.7.5 | QA Certification | 8/10/2005 8:00 | 8/16/2005 17:00 | 5 days | Latricia Simon[90%] |
| 3.7.6 | FCC Approval Testing | 7/20/2005 8:00 | 10/11/2005 17:00 | 60 days | FCC Test Lab,Latricia Simon[10%] |
| 3.7.7 | FCC Approval Paper work | 10/12/2005 8:00 | 1/3/2006 17:00 | 60 days | FCC Test Lab,Latricia Simon[10%] |
| 3.7.8 | FCC Approval Received | 1/3/2006 17:00 | 1/3/2006 17:00 | 0 days | FCC Test Lab,Latricia Simon[10%] |
| 3.7.9 | FCC Labeling | 12/21/2005 8:00 | 1/10/2006 17:00 | 15 days | Printers,Latricia Simon[10%] |
| 3.7.10 | STATags ready for Real World Testing | 1/10/2006 17:00 | 1/10/2006 17:00 | 0 days |  |
| 3.8 | Legal | 1/3/2005 8:00 | 9/9/2005 17:00 | 180 days |  |
| 3.8.1 | Develop EULA | 1/3/2005 8:00 | 1/28/2005 17:00 | 20 days | Lawyer[25%] |
| 3.8.2 | Liability Study | 1/31/2005 8:00 | 5/20/2005 17:00 | 80 days | Lawyer[25%] |
| 3.8.3 | Warrenty Study | 5/23/2005 8:00 | 9/9/2005 17:00 | 80 days | Lawyer[25%] |
| 3.9 | Real-World Testing | 1/11/2006 8:00 | 5/2/2006 17:00 | 80 days |  |
| 3.9.1 | Phase 1 - Ward | 1/11/2006 8:00 | 2/27/2006 17:00 | 34 days |  |
| 3.9.1.1 | Hospital Installation - Ward | 1/11/2006 8:00 | 1/31/2006 17:00 | 15 days | Joseph Williams |
| 3.9.1.2 | Debugging & Enhancements | 2/1/2006 8:00 | 2/21/2006 17:00 | 15 days | Joseph Williams,Francis Deligosa |
| 3.9.1.3 | QA | 2/22/2006 8:00 | 2/27/2006 17:00 | 4 days | Latricia Simon |
| 3.9.2 | Phase 2 - Floor | 2/28/2006 8:00 | 3/30/2006 17:00 | 23 days |  |
| 3.9.2.1 | Hospital Installation - Floor | 2/28/2006 8:00 | 3/13/2006 17:00 | 10 days | Joseph Williams |
| 3.9.2.2 | Debugging & Enhancements | 3/14/2006 8:00 | 3/27/2006 17:00 | 10 days | Joseph Williams,Francis Deligosa |
| 3.9.2.3 | QA | 3/28/2006 8:00 | 3/30/2006 17:00 | 3 days | Latricia Simon |
| 3.9.3 | Phase 3 - Entire Hospital | 3/31/2006 8:00 | 5/2/2006 17:00 | 23 days |  |
| 3.9.3.1 | Hospital Installation - Whole Hospital | 3/31/2006 8:00 | 4/13/2006 17:00 | 10 days | Joseph Williams |
| 3.9.3.2 | Debugging & Enhancements | 4/14/2006 8:00 | 4/27/2006 17:00 | 10 days | Francis Deligosa,Joseph Williams |
| 3.9.3.3 | QA | 4/28/2006 8:00 | 5/2/2006 17:00 | 3 days | Latricia Simon |
| 3.9.3.4 | STATags Ready for Sale | 5/2/2006 17:00 | 5/2/2006 17:00 | 0 days |  |
| 3.10 | Marketing | 10/5/2005 8:00 | 5/2/2006 17:00 | 150 days | Jason Sadler |
| 4 | Phase 3 - Production Out Years | 5/3/2006 8:00 | 12/31/2007 17:00 | 434 days |  |
| 4.1 | Hire Personnel | 5/3/2006 8:00 | 6/13/2006 17:00 | 30 days | Joseph Williams[10%] |
| 4.2 | Product Ramp up | 5/3/2006 8:00 | 8/8/2006 17:00 | 70 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.3 | Full Production | 8/8/2006 17:00 | 8/8/2006 17:00 | 0 days |  |
| 4.4 | Establish Support Department | 6/14/2006 8:00 | 7/11/2006 17:00 | 20 days | Joseph Williams |
| 4.5 | Support Department Established | 7/11/2006 17:00 | 7/11/2006 17:00 | 0 days |  |
| 4.6 | Train Installation Engineers | 6/14/2006 8:00 | 8/8/2006 17:00 | 40 days | Daniel Tubbs,Brian Easton |
| 4.7 | Installation Engineers Trained | 8/8/2006 17:00 | 8/8/2006 17:00 | 0 days |  |
| 4.8 | Marketing/Sales | 6/14/2006 8:00 | 12/31/2007 17:00 | 404 days |  |
| 4.8.1 | Tradeshows | 6/14/2006 8:00 | 12/31/2007 17:00 | 404 days | Sales Staff[15%] |
| 4.8.2 | Publications | 6/14/2006 8:00 | 12/31/2007 17:00 | 404 days | Sales Staff[25%] |
| 4.8.3 | Marketing | 6/14/2006 8:00 | 12/31/2007 17:00 | 404 days | Sales Staff[50%] |
| 4.8.4 | Develop New Markets | 6/14/2006 8:00 | 12/31/2007 17:00 | 404 days | Sales Staff[10%] |
| 4.9 | Support | 7/12/2006 8:00 | 12/31/2007 17:00 | 384 days |  |
| 4.9.1 | Software Updates | 7/12/2006 8:00 | 12/31/2007 17:00 | 384 days | Development Staff |
| 4.9.2 | Warranty Support | 7/12/2006 8:00 | 12/31/2007 17:00 | 384 days | Support Staff[50%] |
| 4.9.3 | Telephone Support | 7/12/2006 8:00 | 12/31/2007 17:00 | 384 days | Support Staff[50%] |
| 4.10 | Plastic Tool Replacement | 8/15/2006 8:00 | 12/31/2007 17:00 | 360 days |  |
| 4.10.1 | Plastic Tool Replacement (every 50000 units) | 9/1/2006 8:00 | 9/28/2006 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.2 | Plastic Tool Replacement (every 50000 units) | 10/2/2006 8:00 | 10/27/2006 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.3 | Plastic Tool Replacement (every 50000 units) | 11/1/2006 8:00 | 11/28/2006 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.4 | Plastic Tool Replacement (every 50000 units) | 12/1/2006 8:00 | 12/28/2006 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.5 | Plastic Tool Replacement (every 50000 units) | 1/1/2007 8:00 | 1/26/2007 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.6 | Plastic Tool Replacement (every 50000 units) | 2/1/2007 8:00 | 2/28/2007 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.7 | Plastic Tool Replacement (every 50000 units) | 3/1/2007 8:00 | 3/28/2007 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.8 | Plastic Tool Replacement (every 50000 units) | 4/2/2007 8:00 | 4/27/2007 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.9 | Plastic Tool Replacement (every 50000 units) | 5/1/2007 8:00 | 5/28/2007 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.10 | Plastic Tool Replacement (every 50000 units) | 6/1/2007 8:00 | 6/28/2007 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.11 | Plastic Tool Replacement (every 50000 units) | 7/2/2007 8:00 | 7/27/2007 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.12 | Plastic Tool Replacement (every 50000 units) | 8/1/2007 8:00 | 8/28/2007 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.13 | Plastic Tool Replacement (every 50000 units) | 9/3/2007 8:00 | 9/28/2007 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.14 | Plastic Tool Replacement (every 50000 units) | 10/1/2007 8:00 | 10/26/2007 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.15 | Plastic Tool Replacement (every 50000 units) | 11/1/2007 8:00 | 11/28/2007 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.16 | Plastic Tool Replacement (every 50000 units) | 12/4/2007 8:00 | 12/31/2007 17:00 | 20 days | Francis Deligosa[10%],Contract Manufacturer[10%] |
| 4.10.17 | Break Even Point | 8/15/2006 8:00 | 8/15/2006 8:00 | 0 days |  |

Management Plan

# Program Identification

This Program Management Plan (PMP) is for the STATag. The program will deliver the STATag hardware, software and documentation for the STATag.

## Program Management Overview

Execution of the Program will be performed in accordance with the procedures defined by the set of planning documents. These documents include Program Management Plan*, System Quality Program Plan (SQPP), Software Management Plan (SMP), Configuration Management Plan (CMP), Engineering Management Plan (EMP), Manufacturing Plan (MP), and Risk Management Plan (RMP) (see Figure 1).

* This Program Management Plan shall be deemed to meet the contractual requirement of a Project Management Plan.

Figure 1. Program Management

This Program Management Plan describes the management philosophy, program organization, schedule, and major milestones that serve as the guide for execution of the Program. The PMP also provides the customer and the quality team with the information they need to monitor and evaluate the progress of the effort. This plan provides the following pertinent information:

- Corporate Organization

- Program Team Organization With Areas of Responsibility

- Work Breakdown Structure

- Program Planning

- Progress Reporting and Team Management

- Detailed Program Schedule and Milestones

- Program Reviews

The Program Management Plan provides guidance for the content and execution of the following plans:

- Risk Management

- Engineering Management

- Software Management

- ILS Support

- Data Management

- Installation

- Configuration Management

- Acceptance Management

## Corporate Structure

The entirety of Digital Inventory Systems Corporation supports the STATag Program.  The following is Digital Inventory Systems STATag Corporate organizational structure:

- CEO & President, Digital Inventory Systems Corporation.

- Group Vice President.

- STATag Program Office. STATag Program Office will execute the program and provide day-to-day senior management supervision, management, engineering, and administrative resources necessary to manage and administer the STATag program.

## Management Approach

Digital Inventory Systems’ management goal is to work closely with the customer to fully understand the system requirements and field a system that meets those requirements. The management approach to executing contracts at Digital Inventory Systems is based on the philosophy that successful Programs are delivered by goal-oriented teams. A Program Manager (PM) will lead the Digital Inventory Systems team. The PM is responsible for all planning, programmatic, technical, and financial aspects of the Program. The PM is the primary Point of Contact (POC) for the customer. The primary duties include supervision of all planning, scheduling, financial, and technical activities, and customer liaison. The PM is responsible for all Program-related decisions and commitments with approval, as required, from the Corporate Management Team.

A key element of Digital Inventory Systems’ program management approach is customer involvement. Digital Inventory Systems encourages the customer to retain an active role in monitoring the progress of all aspects of the Program. The customer is encouraged to discuss technical details directly with members of the Program team, provide planning and schedule recommendations, and assist in resolution of technical and programmatic issues. In order to facilitate customer involvement, Digital Inventory Systems will provide access to program information including, but not limited to:

- program plans and schedules

- program status

- earned value

- formal review material

- action items

- system drawings and documentation

## Program Team

The Program Team is committed to provide the best value by delivering COTS, open architecture, and low-risk systems at the lowest cost. This commitment is attainable because it is based on the re-use of existing technology that is field-proven. Through strategic teaming and an extensive system selection process, Digital Inventory Systems has assembled a cohesive Program Team that is experienced with the implementation of each component that will comprise the STATag Total Ship Computing Environment.

Project Lead. Overall management responsibility for STATag is assigned to a Project Lead who is responsible for planning and coordination of the day-to-day technical, contractual, and financial aspects of the program. He is responsible for the generation and management of all program schedules, for the coordination of program staff assignments and for coordinating all program activities. His principal assistants are:

- Manufacturing Director.  The Manufacturing Director is responsible for all system electronics hardware components, production, and test activities at Digital Inventory Systems. He will ensure production, testing, and installation schedules. The Production Manager is assigned responsibility to provide technical oversight during installation phase, Set-to-Work, and formal testing. His primary responsibilities include coordination of installation plans; managing the configuration, and developing system level installation documentation.

- Personel Director.  The Personal Director administers the personnel and contract workers hired at Digital Inventory Systems.  In addition to supporting the Project Lead he is primarily responsible for the selection, recommendation, orientation, and training of all new employees.  He is involved in the oversight of the team of installation engineers, the support help desk, and all contractual workers throughout the project.

- Marketing and Web Development Director.  The Marketing and Web Development Director is primarily responsible for market analysis, marketing of the STATag, marketing decisions, the sales team and all customer relations prior to installation.  He will also oversee the development of the STATag and Digital Inventory Systems marketing web site.

- Research and Development / Quality Assurance Director.  The Research and Development / Quality Assurance Director is primarily responsible for the oversight and evaluation of all research, prototype development, production prototype development, software development, quality assurance, and research documentation.  Additionally, they are responsible for accurate and timely documentation of all research and development activities.

- Financial Director. The Financial Directory is primarily responsible for the oversight of all financial activities of the STATag team and Digital Inventory Systems.  The FD is responsible for oversight of the Office Manager, the Customer Accounts Manager, and the Accounts Receivable.  They will work closely with the Project Lead to provide accurate financial information and they will ensure accurate and timely financial reporting.  They will ensure the STATag team is on schedule and within the provided budget.

## Program Duration

The STATag program is a 4-year project through delivery of fully integrated STATag systems in approximately 300 hospitals. The Phase 0 schedule consists of a preliminary design down selection milestone in the first quarter of 2004.  To be completed at the end of the second quarter of 2004.  Phase 1 is primarity the prototype fabrication phase and will begin in the third quarter of 2004 and end in the fourth quarter of 2004.  Phase 2 is primarily the product development phase and will last from the first quarter of 2005 to the end of the second quarter of 2006.  Phase 3 is open ended and will begin at the end of phase 2 in the second quarter of 2006.

# Work Breakdown Structure

The program Work Breakdown Structure (WBS) reflects the budgeted cost versus resources required to complete each task. The WBS phase numbers are integrated as part of the master program schedule. Budgets for work planned are entered into Digital Inventory Systems’ financial tracking system for each WBS element, actual costs and estimates to complete are managed by the Program Manager. The WBS element numbers will be structured according to the Contract Statement of Work and will be used to track program costs, progress, earned value and progress relative to the master program schedule. The WBS management tool that Digital Inventory Systems will use is Microsoft Project 2003.

# Program planning

The Digital Inventory Systems Team Lead will maintain the program master schedule. The master schedule contains a line item for each WBS element and will be used to track the progress of each element. All deviations from the master schedule must be coordinated with the program office. It is the responsibility of each team member to call attention to possible schedule deviations at the earliest opportunity. The team lead will coordinate the program schedule with the STATag team members. The program will be developed in phases; within each phase, formal reviews will play an integral part in monitoring program progress. All formal reviews will be announced four weeks in advance of the starting date.

Digital Inventory Systems will take a “top down approach” to the Program Schedule, meaning that we will pace our workload to fit the overall Program requirements. Particular attention will be given to timely milestone completions. It is recognized that the schedule is particularly tight, containing critical program milestones during the first year, and adequate personnel will be available in order to keep the program moving forward.

# Progress PERFORMANCE ASSESSMENT

All Digital Inventory Systems Team members will participate in progress reporting and team management. Digital Inventory Systems will track technical and financial progress of the program. Reviews will be held monthly or as mutually agreeable between Digital Inventory Systems team members.

- Report on progress to date

- Present work to be performed during the next month

- Present status of all deliverables and review planned delivery dates

- Plan and coordinate activities

- Discuss technical or programmatic issues as necessary.

In preparation for the meetings the Digital Inventory Systems Program Manager will collect the current status data on relevant on-going activities, progress against schedule and budget, and planned activity for the next reporting period. Quality reviews of all program documentation and procedures will be held periodically. In particular, the quality program will be involved with program deliveries and milestones and will work off of the master program schedule to plan program audits. Technical, financial and quality progress and status reporting will be conducted according to the following general guidelines.

## Technical Progress and Reporting

The schedule for the program is established during the planning phase and monitored throughout the performance period. The schedule contains an entry for each WBS element. The percentage of completion for each WBS element is determined as necessary to manage program progress and is reviewed at least quarterly during the General Manager’s review.

## Financial Management and Reporting

The financial profile for the Program is established during the planning phase and monitored throughout the performance period. This profile is generated by assigning accounting phase numbers to every Program activity that has been identified as a scheduled event. A budget representing labor costs, materials purchase, and other expenditures (such as travel expenses) is then prepared for every phase. The schedule and budgets are then integrated to provide a spending profile for the phase. The Program spending profile represents a summary of phase spending profiles.

The Team Lead is provided an information package that identifies the phase numbers assigned to each activity, the corresponding budgets and schedules, the overall spending profile for the program, and a synopsis of all major deliverables and milestones specified in the contract. The Team Lead uses this information, combined with an on-line financial summary of the Program to track its financial status on a weekly basis. An updated spending profile is provided automatically by the Financial Director on a monthly basis, or upon request from the Team Lead. The Team Lead uses the financial summary in conjunction with his assessments of technical progress to track the overall status of the efforts.

## Earned Value

Earned Value Ratios will be reported as required. At a minimum, Digital Inventory Systems will determine earned value quarterly at the overall Program level and will report at the 2nd level of WBS indenture in order to provide additional information.

Ratios will be reported in the form of the Schedule Performance Index (SPI) and the Cost Performance Index (CPI). Ratios below 0.90 will be explained in further detail.

SPI is to be calculated as follows:

SPI =	BCWP (Budgeted Cost of Work Performed)

BCWS (Budgeted Cost of Work Scheduled)

CPI is to be calculated as follows:

CPI =	BCWP (Budgeted Cost of Work Performed)

ACWP (Actual Cost of Work Performed)

Digital Inventory Systems will use a combination of its Peachtree Accounting and Microsoft Project Software Programs in order to calculate the ratios. On a monthly basis, actual costs will be downloaded into Project into Peachtree.

## Quality Process and Reporting

Quality management on the program will be a team effort. The Research and Development / Quality Assurance Director will coordinate conduct, quality reviews, and audits. The Team Lead is ultimately responsible for the development and implementation of the System Quality Program Plan. The SQPP is an umbrella plan which incorporates the quality programs of the program team members. The SQPP describes a team quality concept, including Process Coordination and Quality Evaluators. Team members are responsible for performing the processes required to complete Program tasks. Quality Evaluators are responsible for verifying that the development, production, and handling of all documentation, software, and hardware are performed in accordance with the SQPP and its component processes. The team is also responsible for conducting periodic reviews and evaluations of work-in-process; attending in-house test events, and supporting in-house Program reviews. All planned quality program activities and quality evaluations (internal audits) are submitted to the Team Lead for review.

## Monthly Progress Report

Digital Inventory Systems will submit a monthly progress reports. The report shall cover, at a minimum, the following:

- Progress Summary;

- The variance statement;

- Critical Path Analysis;

- Milestone Deliverables, planned actual and forecast;

- Earned Value Schedule and Cost Performance Indices;

- Dependencies: a ‘critical items list’ of all items, whether or not the Contractor’s direct responsibility, which could jeopardize timely completion of the work or any significant parts of the program;

- Risk Status: update of risk register;

- Look Ahead (Future action and Forecast);

- Resource Profile;

- Work Package/Activities planned, actual & forecast status;

- Milestone/Deliverables planned, actual & forecast status;

- Configuration Change Control issues;

- Quality Actions (Reviews, audits);

- One Page Plans and Reports summarising the above for inclusion in the Purchaser’s monthly report; and

- Commercial: amendments to Contract status report; No later than meeting + 10 working days.

# Reviews

Reviews will play an integral part in the management and monitoring of all phases of the STATag Program. Informal reviews with the Program team members will be held at all levels on a weekly basis to ensure that the program stays on track. Formal technical reviews will be held to ensure that the program is proceeding as planned. The types of reviews, their purpose and presented information are addressed in the following paragraphs.

## Program Management Reviews

Program Management Reviews (PMRs) will be conducted with STATag and subcontract representatives. The first PMR will be conducted in July 2004; thereafter PMRs will be conducted approximately every six months (immediately preceding each technical review). The PMRs are scheduled to discuss programmatic issues related to the development and implementation of the Program. The reviews will provide the opportunity to review the progress of the effort; as well as to conduct milestone reviews of deliverables, and identifies and resolves any issues that may arise during the execution of the tasking.

The Team Lead will ensure that all program-related information required to meet the objectives of the review are prepared and delivered not later than two weeks prior to the scheduled review date. The Team Lead will also be responsible for identifying the Digital Inventory Systems STATag Program Team personnel who will attend the review. The Team Lead will attend all Program Management Reviews. The following information will be prepared in support of each PMR. Recorded during the review and delivered before the completion of the review.

## Technical Reviews

Formal technical reviews will be conducted on the dates specified in the master schedule. The reviews will be held jointly with STATag, Digital Inventory Systems Team members and sub-suppliers as necessary. An agenda and review material will be submitted to STATag two weeks prior to the scheduled meeting. Review meeting minutes will be delivered before the completion of the review. The objectives for each review are outlined below.

Reviews will be held to validate the direction taken for the design, development and test of the system. The System Requirements Review (SRR), Preliminary Design Review (PDR), and Critical Design Review (CDR) will be formal reviews held at Digital Inventory Systems’ facility. The Test Readiness Reviews (TRR) will be formal reviews held prior to HAT & SAT.

System Requirements Review is conducted to ensure that the Program team fully understands the system performance requirements specified in the System/Segment Specification. A detailed review of requirements for the system and each subsystem will be reviewed. The System/Segment Specification (Technical Specification) will be used in the review.

System Design Review is conducted to present and review the system design. System requirement allocation to each system component will be discussed. The general approach to be taken for the integration of each system component will be presented. The documents listed below will be used in the review. This will be an informal review. The data will be included in the PDR.

- System/Segment Design Document

- System Interface Design Document

Software Requirements Review is conducted to review the software specification and interface requirement specifications. This review will be conducted as part of the PDR.

Preliminary Design Review is conducted to present the preliminary design of the Program System. The functional requirements of each subsystem will be discussed in detail. The following documents will be used in the review:

Critical Design Review is conducted to review system integration issues. In particular the review will focus on system interfaces.

Test Readiness Reviews are held to determine if the system is ready to proceed to the next level of test. Test configurations and results from the previous test efforts will be presented. The test report from the previous test will be used in the review. The following TRRs will be performed:

- Prior to FAT

- Prior to HAT

- Prior to SAT

## Quality Reviews

The Team Lead supported by the Research and Development / Quality Assurance Directory will establish the time and identify attendees for all formal reviews. He will also coordinate with the appropriate managers to conduct quality reviews at key program milestones, and in preparation for formal reviews with the customer. Informal peer review and engineering planning meetings will also be held at the discretion of each subsystem manager to discuss technical issues, conduct internal comment reviews, and provide technical guidance to members of the Program team. As part of the quality activities for the program, the quality team will conduct informal reviews to:

- Evaluate the processes used by the Program team members to perform program tasks;

- Evaluate deliverable products for compliance with contract requirements;

- Evaluate work-in-process during engineering reviews;

- Document results of each evaluation; and

Recommend corrective and preventive actions if necessary.

Evaluation Plan

Our company, Digital Inventory System, will conduct evaluations for each phase of STATag’s development.  These evaluations will contain a checklist of deliverables needed at the end of each phase. During these evaluations we will track our progress to date then re-evaluate future productions and address any technical issues or risk that have risen.  We plan to evaluate our efficiency in maintaining our scheduled budget, and its impact on our business’s present and future success. In addition to this, we plan to track our product’s impact on our customers in respect to its optimization within their system.

Our project plan will continually be evaluated at the end of each phase.  Phase zero will be considered a success when we have secured a SBIR grant.

Phase one will be considered a success when our prototype is fully functional and has passed all testing.

Phase two will be considered a success when we have a real world working model up and running in the hospital.

Phase three will be considered a success when our product reaches full production and our company has reached a break-even point. In addition to this our customers have to reach their break-even point in order to deem this phase a success.

The evaluation plan is as follows:

Program Design Reviews

- Assessment of the project at the end of each phase

Technical Testing

- Evaluate the direction taken in design, development, and testing of the project

  - Prototype testing

  - Integration testing

  - Web interface testing

Quality Testing/Reviews

- Evaluate the processes used by team members to perform tasks

- Evaluate deliverables for completeness at the end of each phase

- Evaluate  any new or pending risks as they occur

Periodical Reporting

- Used to evaluate our efficiency in maintaining our scheduled budget for this project

- Used to evaluate our progress at each phase

Our work break down structure outlines the time schedule we have planned to follow.

Marketing Plan

A market has been opened for STATag with the emergence of reVIEW, a program founded by Cindy Jimmerson that employs the Toyota Production System. This system helps to create a more “defect-free” product or service, reduce or eliminate waste, and improve workplace appreciation. This program was spawned off the top ten wasteful prospects. One of the most wasteful concerns was equipment locating. It has been found that 35 to 60% of a nurse’s time is wasted on, partly, searching for equipment. This figure results in 58 to 99 billion dollars wasted on an annual basis.
	The marketing strategy addresses several facets. The problem with time wasted for locating equipment can be drastically reduced. In a matter of seconds, a hospital employee can learn the location of a particular piece of equipment with the click of a mouse. The benefit of saving hospitals time and money is an incentive in itself. With the acquisition of STATag by a medical facility, a return on investment can be achieved in as little as 8 months, allowing the hospital to return a profit from the system use in the first year. Savings in subsequent years continue to ascend as product usage continues.
	This will provide us with valid arguments when approaching a medical facility as a potential customer. We will be able to show that a hospital will be able to achieve a higher level of service for its patients, and maximize efficiency for profitable gain.
	With the acquisition of funding from SBIR, we will be able to begin realistic marketing strategies. Marketing strategies include medical journals and magazines, web advertising, attendance of medical trade events as well as technological expos and events.
	In addition to the benefits attained by the use of the solution, a medical facility can advertise to its customers that a high level of service and efficiency can be expected. This would encourage facilities without such technology to consider using a product such as STATag to maintain competitiveness.
	STATag will use the IEEE 802.14.5 standard which specifies ultra-low power self configuring wireless networks. A main marketing strategy is the ease in maintenance with such a network. Most wireless networking technologies in medical facilities employ IEEE 802.11, which require administrative overhead. This overhead can be eliminated in IEEE 802.14.5 because of the specification that calls for self discovery on the network. 
	For advertising of the solution, we plan to use $30,000 for booth rental of a trade show, with $4,000 (for four employees) used for airfare. 
For a trade show exhibit, we have considered the Florida International Medical Expo (FIME). FIME is an attractive venue for our solution as it attracts medical experts from across the world, in addition to selling out the 2003 event. 
	We also plan to expand advertising to medical journals. According PERQ/HCI, in 1998, advertising in medical journals topped the response effectiveness at 66.5%.

This concept alone shows that we can obtain market awareness and message penetration with the use of medical journal advertising. Out of the top five rated best journals, the FDA Consumer Magazine published by the FDA would be an obvious choice for our paper and web advertisements.(Note to group – this is a bi-monthly journal)
	It will cost approximately $932,600 to build STATag. $850,000 comes from SBIR grants and another $200,000 will come from an SBA loan.

Competition

The STATag uses an upcoming efficient wireless networking standard that is easy to maintain. Our competitors use technology that requires additional expensive hardware, and includes wireless technology that requires administration overhead. With STATag, no expensive access points are required, and the wireless technology used is self-configuring and self-discovering. This means no time wasted with IT administrative overhead.

|  | Digital Inventory Systems | WhereNet | Intermec | Symbol Technologies |
| --- | --- | --- | --- | --- |
| Provides Real Time Location | X | X |  |  |
| Provides Real Time Location in 3D | X |  |  |  |
| Tag has serial number | X | X | X | X |
| Tag knows location | X |  |  |  |
| Location history when out of building | X* |  |  |  |
| Low cost infrastructure | X |  | X | X |
| Low administrative overhead | X | X |  |  |
| Triggered location update on movement | X |  |  |  |
| Can trigger alarms | X | X | X |  |
| Can detect tag removal | X |  |  |  |
| Allows for update based on local switch | X |  |  |  |

The WhereNet solution only provides 2D locating. It does not address locating devices that are on different floors. WhereNet’s solution also does not keep track of its location. In addition, WhereNet uses 802.11b IEEE standard which requires expensive access points once it has reached the ranges boundaries.

The Intermec solution does not provide any location tracking. Although it can trigger alarms, it is not able to detect tag removal which makes it’s alarm mechanism defeatable.

Symbol Technologies provides no location tracking nor provides any alarm mechanisms. It is assumed that’s its primary function is for inventory tracking alone and not for equipment location.

Funding Plan

The funding for a small startup company is arguably the one of most important aspect of planning.  To that end, the STATag team will be submitting an SBIR Grant proposal for the Phases I and Phases II of product development.  We will be submitting our application for a Small Business Innovation Research (SBIR) grant to the Department of Health and Human Services in order to establish our development on sound financial footing.  Our SBIR application requests approximately $100,000 for Phase I development.  Phase I will last approximately 4 months and our team will be primarily focused on the development of our prototype.  We are additionally requesting $750,000 for Phase 2 of our project.  During phase 2 our team will develop a real-world version of the STATag system and we plan to implement the Real Time Equipment Tracking in a test hospital.

Following phases 1 and 2 we anticipate receiving funding from Federal Small Business Administration backed loan and sales revenue from completed STATag systems.  These funding sources will provide the funds for phase 3, our production ramp-up phase.  From the beginning of phase 3 on our primary funding source will be STATag sales, installation, and support revenue.  We will require $200,000 start-up capital from a funding organization before the beginning of phase 3.  During phase 3 our goal will be to repay the loan, build a customer base, and increase sales to approximately 20 hospitals a month.  Following phase 3 we anticipate being a financially self-sufficient company turning an estimated profit of $75,000,000 at the end of that phase.  At that time we expect to expand into additional inventory tracking markets.

We are anticipating, at this time, to proceed from SBIR Grant money to becoming a self-sufficient company.  However, the possibility of being either acquired or invested in by a larger company is a distinct possibility our team is receptive to.  Possible companies that would take a financial interest in the STATag and the Real Time Equipment Tracking technology include medical supply companies, medical equipment manufacturers, and current inventory tracking solution providers.  There are, however, currently no offers for acquisition of our product or company at this time.

The STATag is, in our opinion, a very viable product and a sound investment.  As our financial plan currently stands we anticipate being able to develop the STATag in the financial and time constraints previously stated.  We believe that this product will revolutionize inventory tracking in not only the medical equipment market but in any market for which it is introduced.   The following are the proposed budgets for phases I to III.

Staffing Plan

Initial Staff

Project Lead

The project lead is instrumental in managing the direction, resources, and personnel of the project.  He is responsible for upper management for the progress of the project; in addition, the project lead has the final word over any department decision, and thus must have experience in dealing with the various departmental operations of his team.

Manufacturing Director

The manufacturing director is responsible for the planning of the production schedule within budgetary limitations and time constraints.  This includes analyzing the project’s personnel and resources, and selecting the best way to meet the production quota.  The manufacturing director will determine which machines to be used, and the sequence of production.  Also, manufacturing duties will include monitoring the production to make sure it stays on schedule and correcting any problems that may arise.

Personnel Manager

The personnel manager is responsible for making sure the team gets the best from the people who work for them.  This role is characterized by a manager involved in selecting the right sort of staff and promoting practices which ensure they are managed effectively.  This includes recruitment and selection of staff which includes drawing up job descriptions, preparing advertisements, and checking application forms.  The personnel manager will aid in employee relations, employee services, pay and benefits, and human resource planning.

Quality Assurance / R&D Manager

The quality manager will monitor products and documentation to ensure they meet specifications and standards of presentation and quality.  This includes the following tasks:

-Study product specifications

-Sample products to determine whether they meet specifications and quality standards, and take corrective action if necessary

-Analyze quality assurance data, and make recommendations for improvement.

-Train and assist operators to carry out their quality control functions.

Financial Manager

The financial manager will plan, organize, direct, control and evaluate the operation of financial and accounting departments. Managing duties include developing and implementing the financial policies and systems of establishments. This includes establishing the budget and making sure the team stays within the budget.

Marketing Director

The marketing director will design, implement, and facilitate annual marketing plan for the team, and is responsible for the development of the overall plan for how to approach the market. Marketing strategies will be to support and facilitate development and implementation of section business/marketing plans. Also, the director will plan and administer the team’s marketing operations budget.

Contracted Staff

Technical Writer

The technical writer is responsible for complete documentation through the project phases.  Duties will include writing project plans, documents, and recording any events taken place during the project process.

Drafter

The drafter is responsible for drawing the final production blueprints of the plastic housing for the STATag.

Computer Engineer

The computer engineer will assist in the design of the lab prototype during phase 1.

Lawyer

The lawyer will conduct legal research, write the EULA and warranty documents, and provide legal advice.

Hired Staff

Office Manager

The office manager will organize and supervise all of the administrative activities that take places in the office.  The main goal of the office manager is to keep the office running efficiently and smoothly which includes arranging meetings, delegating work, and supervising the work of the staff.

Software Engineer

The software engineer is in charge of designing, coding, and debugging all software related to the development of the system as well as the necessary encryption to keep the data secure.

Installation Engineer

The installation engineer will be solely responsible for installation of the STATags in hospitals.  Planning of this installation will require the engineer to plan out the mapping process of the building including precise placement of tracking tags in order to monitor position of the STATags.

Network Engineer

The network engineer will be responsible for setting up and maintaining all DIS owned computers and servers, including cabling, network switches, servers, workstations, operating systems, and applications.

Accounts Manager

The accounts manager will be responsible for the company accounting and the accounting staff (if hired after phase 3).

Accounts Receivable

The accounts receivable person will be responsible for prompt billing and the record keeping associated with billing.

Help Desk Coordinator

The help desk coordinator will be responsible for training, supervising, and scheduling the tech support personnel.

Tech Support

The tech support personnel will be responsible for answering the phones and assisting customers by answering questions and assisting troubleshooting.

Inventory Manager

The inventory manager will be in charge of delegating the distribution of the inventory.

Sales Manager

The sales manager will delegate, organize, and lead the sales team.  The overall responsibility of the sales manager is to make sure all sales reach their goals.  Duties will include recruiting and training sales staff, supervising and monitoring the sales team, and establishing sale goals.

Salesman

The salesman’s job will be to sell the product during different business ventures.  Duties will include speaking at conferences or tradeshows to convince the public to buy our product.  The overall responsibility of the salesman is to find buyers and meet the sale goal.

Resource Plan

Our resource plan will be developed throughout three phases.  During the first phase, resources will consist mainly of office equipment and prototype development equipment.  The second phase will consist of additional office and prototype testing equipment.  Finally in the third phase, budget resources will be allocated towards the expansion of the business.

For the first phase, we have allocated 36,000 dollars toward essential office and prototype resources.  With this money we will purchase and furnish the office.  In furnishing the office we will purchase computers and the necessary software components, along with telephones and a network server.  In addition to this we will buy the prototype parts and electrical equipment to test the hardware components.

Phase two we have allocated 264,750 dollars for office, and marketing expansion.  Along with this we have allocated some of the funds toward developing the prototype.  For the office we will expand and add more furniture, more computers, and more Internet components.  We will begin an extensive market campaign, which will cause us to buy rental booths and advertising spots in tradeshow productions.   In addition to this we will have to buy testing and tooling equipment for our prototype. Office, prototype and market develop are where we have projected our resource to encompass.

The last phase, phase three, we have allocated 701,600 dollars towards the expansion of production and our marketing.  Production expansion includes expanding our office, and purchasing more tooling supplies. The marketing expansion includes airfare and car rentals at distant locations, and website site hosting.

As we anticipate expansion of our business, we need to anticipate expansion everywhere.  Throughout each phase we have accounted for staff, production and marketing to increase.  By thinking ahead about the necessary resources in each of these areas we have eliminated potential expansion problems.

Budgets

|  | Phase 1 |  |
| --- | --- | --- |
| Phase Length (Months) |  |  |  | 4 |  |
| Overhead |  | Units | Cost | Qty | Sub-Total |
|  | Office Space 2600 Sq. Feet | Month | $1,800 | 4 | $7,200 |
|  | Utilities | Month | $500 | 4 | $2,000 |
|  | Telephone/Internet | Month | $400 | 4 | $1,600 |
|  | Office Furniture | One-Time | $6,000 | 1 | $6,000 |
|  | Electrical Eng. Equipment | One-Time | $2,500 | 1 | $2,500 |
|  | Office Computers | One-Time | $8,000 | 1 | $8,000 |
|  | Peachtree 2004 | One-Time | $1,000 | 1 | $1,000 |
|  | Network / Server | One-Time | $3,500 | 1 | $3,500 |
|  | MS Visio / MS Project | One-Time | $3,000 | 1 | $3,000 |
| Total Overhead |  |  |  |  | $34,800 |
| Marketing | Web Site Hosting | Month | $50 | 4 | $200 |
|  | Jason Sadler - Marketing Director | Month | $2,250 | 4 | $9,000 |
| Total Marketing |  |  |  |  | $9,200 |
| Prototype Development | Drafter (plastic parts) | Hourly | $30 | 20 | $600 |
|  | Computer Engineer | Hourly | $60 | 100 | $6,000 |
|  | Prototype Parts | One-Time | $1,000 | 1 | $1,000 |
| Total Electrical |  |  |  |  | $7,600 |
| Manufacturing | Francis Doligosa - Manufacturing Director | Month | $2,250 | 4 | $9,000 |
| Total Manufacturing |  |  |  |  | $9,000 |
| Management | Daniel Tubbs - Team Manager / Computer Engineer | Month | $2,250 | 4 | $9,000 |
|  | Joseph Williams - Personnel Manager | Month | $2,250 | 4 | $9,000 |
|  | Latricia Simon - R & D Manager / QA Manager | Month | $2,250 | 4 | $9,000 |
|  | Brian Easton - Finance Officer | Month | $2,250 | 4 | $9,000 |
| Total Management |  |  |  |  | $36,000 |
| Total Phase 1 Costs |  |  |  |  | $96,600 |

|  | Phase 2 |  |
| --- | --- | --- |
| Phase Length (Months) |  |  |  | 17 |  |
| Overhead |  | Units | Cost | Qty | Sub-Total |
|  | Office Space 2600 Sq. Feet | Month | $1,800 | 17 | $30,600 |
|  | Utilities | Month | $500 | 17 | $8,500 |
|  | Telephone/Internet | Month | $400 | 17 | $6,800 |
|  | Office Furniture | Per Hire | $1,000 | 6 | $6,000 |
|  | Office Computers | Per Hire | $2,000 | 6 | $12,000 |
|  | Network / Server | Per Hire | $1,000 | 6 | $6,000 |
|  | Development Software | Per Hire | $1,000 | 8 | $8,000 |
| Total Overhead |  |  |  |  | $77,900 |
| Marketing | Web Site Hosting | Month | $50 | 17 | $850 |
|  | Jason Sadler - Marketing Director | Month | $3,500 | 17 | $59,500 |
|  | Graphics Designer | Hourly | $40 | 40 | $1,600 |
|  | Trade Show Booth Rental | One-Time | $30,000 | 1 | $30,000 |
|  | Trade Magazine Ad | One-Time | $11,000 | 5 | $55,000 |
|  | Airfare to Tradeshow | One-Time | $2,000 | 2 | $4,000 |
|  | Car Rental | One-Time | $400 | 1 | $400 |
|  | Hotel | One-Time | $500 | 2 | $1,000 |
|  | Entertainment | One-Time | $500 | 2 | $1,000 |
| Total Marketing |  |  |  |  | $153,350 |
| Prototype Development | Test WWW Server | One-Time | $2,500 | 1 | $2,500 |
|  | Test DB Server | One-Time | $2,500 | 1 | $2,500 |
|  | Test Workstations | One-Time | $3,000 | 1 | $3,000 |
|  | Plastic Tooling | One-Time | $20,000 | 2 | $40,000 |
|  | Production Engineering | One-Time | $15,000 | 1 | $15,000 |
|  | Test Run | Per Tag | $50 | 100 | $5,000 |
|  | FCC Approval Testing | One-Time | $20,000 | 1 | $20,000 |
| Total Prototype |  |  |  |  | $88,000 |
| Software | Software Engineer 2 | Month | $4,500 | 17 | $76,500 |
|  | Technical Writer | Month | $3,500 | 2.5 | $8,750 |
|  | Error Reporting Software | One-Time | $50 | 100 | $5,000 |
| Total Software |  |  |  |  | $90,250 |
| Manufacturing | Francis Deligosa - Manufacturing Director | Month | $3,500 | 17 | $59,500 |
| Total Manufacturing |  |  |  |  | $59,500 |
| Management | Daniel Tubbs - Team Manager | Month | $4,000 | 17 | $68,000 |
|  | Joseph Williams - Personnel manager | Month | $3,500 | 17 | $59,500 |
|  | Brian Easton - Finance Manager | Month | $3,500 | 17 | $59,500 |
|  | Latricia Simon - R&D Manager / QA Manager | Month | $3,500 | 17 | $59,500 |
|  | Office Manager | Month | $2,500 | 17 | $42,500 |
|  | Lawyer | Hour | $300 | 180 | $54,000 |
| Total Management |  |  |  |  | $343,000 |
| Hospital Installation | Installation Engineer | Month | $4,000 | 3 | $12,000 |
|  | Network Engineer | Month | $4,000 | 3 | $12,000 |
| Total Hospital Installation |  |  |  |  | $24,000 |
| Total Phase Cost |  |  |  |  | $836,000 |

|  | Phase 3 |  |
| --- | --- | --- |
| Phase Length (Months) |  |  |  | 20 |  |
| Overhead |  | Units | Cost | Qty | Sub-Total |
|  | Office Space 6000 Sq. Feet | Month | $4,000 | 20 | $80,000 |
|  | Utilities | Month | $1,000 | 20 | $20,000 |
|  | Telephone/Internet | Month | $600 | 20 | $12,000 |
|  | Office Furniture | One-Time | $1,000 | 10 | $10,000 |
|  | Office Computers | One-Time | $2,000 | 10 | $20,000 |
|  | Network / Server | One-Time | $1,000 | 10 | $10,000 |
|  | Development Software | One-Time | $1,000 | 10 | $10,000 |
| Total Overhead |  |  |  |  | $162,000 |
| Marketing | Web Site Hosting | Month | $50 | 20 | $1,000 |
|  | Jason Sadler - Marketing Director | Month | $4,000 | 20 | $80,000 |
|  | Trade Show Booth Rental | One-Time | $30,000 | 4 | $120,000 |
|  | Trade Magazine Ad | One-Time | $11,000 | 4 | $44,000 |
|  | Airfare to Tradeshow | One-Time | $2,000 | 16 | $32,000 |
|  | Car Rental | One-Time | $400 | 4 | $1,600 |
|  | Hotel | One-Time | $500 | 16 | $8,000 |
|  | Entertainment | One-Time | $500 | 16 | $8,000 |
| Total Marketing |  |  |  |  | $294,600 |
| Sales | Sales Manager | Month | $7,000 | 20 | $140,000 |
|  | East Coast Sales | Month | $6,000 | 20 | $120,000 |
|  | West Coast Sales | Month | $6,000 | 20 | $120,000 |
|  | Midwest Sales | Month | $6,000 | 20 | $120,000 |
|  | East Coast Sales | Month | $6,000 | 20 | $120,000 |
|  | West Coast Sales | Month | $6,000 | 20 | $120,000 |
|  | Midwest Sales | Month | $6,000 | 20 | $120,000 |
| Total Sales |  |  |  |  | $860,000 |
| Development | Software Engineer 1 | Month | $4,000 | 20 | $80,000 |
|  | Software Engineer 1 | Month | $4,000 | 20 | $80,000 |
|  | Software Engineer 1 | Month | $4,000 | 20 | $80,000 |
| Total Development |  |  |  |  | $240,000 |
| Manufacturing | Francis Deligosa - Manufacturing Director | Month | $4,000 | 20 | $80,000 |
|  | Inventory Manager | Month | $3,000 | 20 | $60,000 |
|  | Retool Plastic Mold | Per 50000 | $20,000 | 16 | $320,000 |
| Total Manufacturing |  |  |  |  | $460,000 |
| Management | Daniel Tubbs - Team Manager | Month | $5,000 | 20 | $100,000 |
|  | Joseph Williams - Personnel manager | Month | $4,000 | 20 | $80,000 |
|  | Latricia Simon - R&D Manager / QA Manager | Month | $4,000 | 20 | $80,000 |
|  | Brian Easton - Finance Manager | Month | $4,000 | 20 | $80,000 |
|  | Office Manager | Month | $3,500 | 20 | $70,000 |
|  | Accounts Manager | Month | $4,000 | 20 | $80,000 |
|  | Accounts Receivable | Month | $3,500 | 20 | $70,000 |
| Total Management |  |  |  |  | $560,000 |
| Installation Department | Lead Installation Engineer | Month | $5,000 | 20 | $100,000 |
|  | Installation Engineer | Month | $4,500 | 20 | $90,000 |
|  | Installation Engineer | Month | $4,500 | 20 | $90,000 |
|  | Installation Engineer | Month | $4,500 | 20 | $90,000 |
|  | Installation Engineer | Month | $4,500 | 20 | $90,000 |
|  | Installation Engineer | Month | $4,500 | 20 | $90,000 |
|  | Installation Engineer | Month | $4,500 | 20 | $90,000 |
| Total Hospital Installation |  |  |  |  | $640,000 |
| Support Department | Help Desk Coordinator | Month | $3,000 | 20 | $60,000 |
|  | Tech Support | Month | $2,500 | 20 | $50,000 |
|  | Tech Support | Month | $2,500 | 20 | $50,000 |
|  | Tech Support | Month | $2,500 | 20 | $50,000 |
|  | Ticket Tracking Software | One-Time | $5,000 | 1 | $5,000 |
| Total Hospital Installation |  |  |  |  | $215,000 |
| Total Phase Cost |  |  |  |  | $3,431,600 |

- Human Subjects: Not Applicable

No human subjects are involved in this project.

- Vertebrate Animals: Not Applicable

No vertebrate animals are involved in this project.

- Literature Cited

- Mark Murphy, Research Brief: Eliminating Wasteful Work in Hospitals Improves Margin, Quality and Culture, Murphy Leadership Institute, 2003

- Hospital Statistics, American Hospital Association, 2004

- Cost of Caring: Key Drivers of Growth in Spending on Hospital Care, PriceWaterhouseCoopers, 2003

- Cindy Jimmerson, RN, Dorthy Weber, MSW, and Durward Sobek, PhD, Reducing Waste and Errors: Piloting Lean Principles at IHC, not yet published.

- Consortium/Contractual Agreements

None consortium/contractual agreements are involved in this project.

- Letters of Support

None.

- Product Development Plan: Not Applicable

SBIR/STTR Phase II and Fast-Track only.